Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below, you will find different fields that you must complete with the requested information.

| APT Project Progress Summary | During the development of the project, we have progressed through all the activities established in our work plan. We began with the project analysis stage, where we identified the problem, the proposed solution, the scope and stakeholders, in addition to conducting surveys with older adults to learn their opinions about our project. We then continued with the requirements specification phase, where we identified both the functional and non-functional requirements of the project, as well as creating user stories and business rules. We then moved on to the third phase, system design, which included the architecture, database, mockups and security. We also conducted another survey to learn the opinions of older adults about the application design and what they would change and/or add. For the fourth phase, we carried out the agile planning of the project, first defining the epics, Product Backlog, deliverables, User Story Map and Release Plan. Once this was completed, we began the four Sprints, each including Sprint Planning, Sprint Backlog, Daily Meetings, Sprint Review and the project Retrospective. In the first Sprint we focused on system design activities, in the second on the database, in the third we began developing the functionalities and, finally, in the fourth Sprint we carried out the complete system integration. |
| --- | --- |
| Objectives | The general objective of the project did not require any changes; however, we added the following specific objectives: - Different games to provide entertainment and stimulation activities for older adults. - Voice instructions for older adults with visual difficulties - Color-blind mode for greater accessibility. We also removed one of the specific objectives because it requires a higher level of monitoring than we can currently provide: - Detect unusual behavior (for example, if the person has not left the room for many hours or has walked excessively). |
| Methodology | The methodology defined at the beginning did not require any adjustments. |

| Progress Evidence | The evidence presented below supports our progress in the development of the project, as it includes completed activities, documents, designs, planning artifacts and the final product we developed, allowing all the work carried out to be visualized. The main pieces of evidence are the following: - Problem and analysis document: It allowed us to identify the problem and the solution we intended to address. - Project evaluation document: It demonstrates the analysis carried out to determine the feasibility and viability of the project. - Project Charter: It allowed us to demonstrate the initial formalization of the project, its objectives and scope. - Stakeholder register: It allowed us to identify the people and groups related to the project and consider their needs. - Gantt Chart: It allowed us to demonstrate the planning of the activities, timeframes and stages considered for the development of the project. - Mind Map: It allowed us to represent and organize the main ideas and elements related to the solution. - Product definition: It shows the characteristics, objectives and scope defined for the solution. - Requirements list: It allowed us to demonstrate the identification and definition of the needs that the system must meet. - User stories: It demonstrated the transformation of requirements into functionalities from the users' perspective. - Architecture: It demonstrated the technical planning of the solution and the structure of the application. - Database: It demonstrated the technical planning of the solution and the structure required to store and manage information. - Mockup: It demonstrated the interface design and the organization of the application's main functionalities. - Agile management documents: They demonstrated the use of the Scrum methodology through elements such as the Product Backlog, Sprint Backlog, Sprint Planning and development monitoring. - Test plan: Planning of the tests required to verify the correct operation of the solution. - Error log: It demonstrated the identification, monitoring and correction of issues found during development and testing. - Economic evaluation: It provided evidence of the cost analysis and economic viability of the project. - Installation manual: Procedures required to install and configure the solution. - User manual: It describes how the application works and guides users in the use of its main functionalities. - Continuity and maintenance plan: Considerations for maintaining the system and ensuring its continuity after implementation. - Completed app: The result of the development, allowing the implementation of the defined functionalities to be verified. - Final Report: Results and conclusions obtained during the development of the project. |
| --- | --- |

2. Work Plan Monitoring

Carefully review your work plan, focusing especially on the progress status and adjustments columns.

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Responsible person | Observations | Progress status | Adjustments |
| List the competencies or competency units related to the different activities required for the development of the APT project. | List the activities required to develop the APT project. | List the resources required to carry out the defined activities. | Indicate the duration of each activity. | Write the name of the team member responsible for each activity. | Indicate the difficulties or facilitating factors that could arise during the execution of each proposed activity. | Describe the progress status of each activity. Status types: In progress / Delayed / Not started / Completed / Adjusted | Indicate the adjustments or reformulations you have made. |
| Project management | Problem and solution analysis | Problem information, documentation, computer, analysis tools. | 5 days | Ortiz / Hidalgo | There may be difficulties in defining the scope correctly, but having information about the problem and target users is a facilitator. | Completed | No adjustments were made |
| Project evaluation. | Project evaluation. | Project information, office tools, technical documentation. | 4 days | Paul Hidalgo | It requires correctly estimating the available resources and time to avoid an unrealistic scope. | Completed | No adjustments were made |
| Project management | Project Charter | Project Charter template, project documentation, computer. | 5 days | Hidalgo / Cornejo | It facilitates the initial organization of the project and the clear definition of objectives. | Completed | No adjustments were made |
| Project management | Stakeholder identification | Stakeholder matrix, project information, computer. | 2 days | Melanie Ortiz | It can be complex to identify all users involved and their needs. | Completed | No adjustments were made |
| Project management | Discovery and vision. | Project information, office tools and analysis tools. | 4 days | Angel Rengifo | The survey and information gathering with users will help validate the needs initially identified. | Completed | No adjustments were made |
| Project management | Product definition | Analysis and project management tools. | 3 days | Melanie Ortiz | Consistency must be maintained between the objectives, scope and prioritized functionalities. | Completed | No adjustments were made |
| Project management | Functional Requirements | Computer, internet, interviews, meetings with users, project documentation, tools for recording requirements. | 2 days | Ortiz / Hidalgo | It may require constant adjustments due to changes in user needs. | Completed | No adjustments were made |
| Project management | Non-Functional Requirements | Computer, internet, interviews, meetings with users, project documentation, tools for recording requirements. | 2 days | Héctor Cornejo | It may require constant adjustments due to changes in user needs. | Completed | No adjustments were made |
| Agile project management | Creation of user stories. | Computer, identified requirements, project management tools, project documentation. | 3 days | Ortiz / Rengifo | The main system functionalities must be prioritized correctly. | Completed | No adjustments were made |
| Project management | Business rule specification. | Computer, identified requirements, project management tools, project documentation | 1 day | Héctor Cornejo | The rules must be consistent with the older adult and caregiver roles and with the defined functionalities. | Completed | No adjustments were made |
| Software Architecture | Architecture design | Computer, technical documentation, architecture diagrams, modeling tools, requirements documentation. | 2 days | Rengifo / Hidalgo | The architecture and technologies to be used must be selected correctly. | Completed | No adjustments were made |
| Database | Database modeling. | Computer, system requirements, modeling tool, entity-relationship diagrams, technical documentation. | 2 days | Angel Rengifo | It requires correctly analyzing the system entities and relationships. | Completed | No adjustments were made |
| Database | Database design | Computer, data model, database management system, modeling tool, technical documentation. | 2 days | Angel Rengifo | It may require adjustments according to changes in the requirements. | Completed | No adjustments were made |
| Software design | Mockup creation | Computer, interface design tool, requirements, visual references, project documentation. | 2 days | Ortiz / Hidalgo / Cornejo | It may require several iterations to improve the user experience. | Completed | No adjustments were made |
| Systems security | Security design | Computer, technical documentation, requirements, security best practices, authentication system and Supabase. | 3 days | Angel Rengifo | Data protection, access control and role separation must be considered. | Completed | No adjustments were made |
| Agile project management | Epic development | Product Goal, requirements, user stories, Product Backlog and management tools. | 2 days | Hidalgo / Cornejo | The epics must represent coherent groups of functionalities and later be divided into user stories. | Completed | No adjustments were made |
| Agile project management | Product Backlog creation and prioritization. | Computer, user stories, project management tool, Product Backlog, prioritization criteria. | 2 days | All | It makes it possible to verify that the functionalities are aligned with the project objectives. | Completed | No adjustments were made |
| Agile project management | Definition of deliverables | Project documentation, Product Backlog, planning, computer and office tools. | 1 day | Melanie Ortiz | The deliverables must be consistent with the established scope and objectives. | Completed | No adjustments were made |
| Agile project management | User Story Map | User stories, Product Backlog, management tools and project documentation. | 1 day | Ortiz / Cornejo | It facilitates understanding the overall product flow and prioritizing functionalities. | Completed | No adjustments were made |
| Agile project management | Release Plan | Product Backlog, prioritized user stories, project planning and schedule. | 2 days | Melanie Ortiz | It must consider the available scope, priorities and development time. | Completed | No adjustments were made |
| Agile project management | Sprint Planning | Computer, validated Product Backlog, project management tool, work schedule, effort estimates. | 1 day | All | There may be difficulty estimating the development time for each task. | Completed | No adjustments were made |
| Agile project management | Sprint Backlog | Computer, Product Backlog, prioritized user stories, project management tool, task estimates. | 1 day | All | It allows tasks to be organized according to priority and required effort. | Completed | No adjustments were made |
| Agile project management | Daily Meetings | Computer, schedule, communication tool and task board. | 20 days | All | It helps detect blockers early and keeps the team coordinated. | Completed | The activity duration was adjusted because we changed from 2 to 4 Sprints. |
| Software design | System design | Computer, Product Backlog, design tools | 5 days | All | First development Sprint of the project; difficulties may arise if users do not like the design. | Completed | The design activity was added because during the process we only had one development activity. |
| Mobile Programming, database, systems integration | Database development | Computer, Product Backlog, database development and programming tools | 5 days | All | Second Sprint, which will be facilitated by the tools and the design completed in stage 4. | Completed | It was added because we had not considered database development, only functionality development. |
| Mobile Programming, database, systems integration | System development | Development computer, development environment, IDE, mobile framework, code repository, technical documentation. | 5 days | All | Main stage of the project. It may present technical challenges during implementation. | Completed | The activity duration was adjusted. |
| Mobile Programming, database, systems integration | System integration | Computer, Product Backlog, systems integration tools | 5 days | All | Final Sprint of the project; it may be difficult due to possible incompatibilities, etc. | Completed | It was added because we had not considered an integration activity, only functionality development. |
| Agile project management | Sprint Review | Computer, developed application, Sprint Backlog, Sprint results, project documentation, stakeholders. | 1 day | All | It facilitates receiving feedback and validating project progress. | Completed | No adjustments were made |
| Agile project management | Retrospective | Computer, project management tool, Sprint results, issue log, team participation. | 1 day | All | It allows improvements to be identified for future development cycles. | Completed | No adjustments were made |
| Software quality | Quality test plan | Computer, requirements documentation, user stories, testing tools, acceptance criteria. | 4 days | All | It requires correctly defining the acceptance criteria and test scenarios. | Not started | No adjustments were made |
| Software quality | Functional Testing | Computer, test devices, application, test cases, testing tools and security analysis. | 5 days | Héctor Cornejo | Complete testing is required to ensure safe operation. | Not started | No adjustments were made |
| Software quality | Non-Functional Testing | Computer, test devices, application, test cases, testing tools and security analysis. | 3 days | Héctor Cornejo | Complete testing is required to ensure safe operation. | Not started | No adjustments were made |
| Software quality | Error correction and adjustments | Development computer, source code, repository, error logs, debugging and testing tools. | 5 days | Héctor Cornejo / Angel Rengifo | The required time may increase depending on the number of errors found. | Not started | No adjustments were made |
| Software quality | Project validation | Application, survey and users. | 2 days | Melanie Ortiz / Paul Hidalgo | The results may lead to adjustments in the solution. | Not started | No adjustments were made |
| Project evaluation, Project management | Economic evaluation and feasibility. | Quotations, calculation tools, infrastructure and software information. | 5 days | Paul Hidalgo | The costs of the tools, services and technologies used must be investigated. | Not started | No adjustments were made |
| Project management | Deployment architecture | Architecture diagram, technical documentation, application, backend, Supabase, deployment services and computer. | 4 days | Angel Rengifo | It must consider communication between the application, backend and database. | Not started | No adjustments were made |
| Project management | Installation manual | Computer, technical documentation, source code, GitHub repository and project configuration. | 4 days | Angel Rengifo | It must allow another person to configure and run the system by following the instructions. | Not started | No adjustments were made |
| Project management | User manual | Completed application, screenshots, computer, documentation and Figma. | 3 days | Héctor Cornejo / Melanie Ortiz | It must consider the differences between the older adult and caregiver roles. | Not started | No adjustments were made |
| Project management | Continuity and maintenance plan | Technical documentation, source code, GitHub, infrastructure information and project planning. | 4 days | Paul Hidalgo / Angel Rengifo | It must consider updates, corrections, information backups and the future evolution of the system. | Not started | No adjustments were made |
| Project management | Project closure. | Computer, final documentation, project reports, results obtained, closure records, project repository. | 1 day | Melanie Ortiz | It considers final documentation, results evaluation and project delivery. | Not started | No adjustments were made |

3. Adjustments Based on Monitoring

Review the observations in your work plan in greater depth. Analyze the planned activities and indicate which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of my work plan: Describe the factors that have facilitated and/or hindered the development of your APT Project so far. In the case of difficulties, describe what actions you took and/or will take to solve them. The agile methodology we incorporated into our project was one of the factors that facilitated the development of our APT project, because it helped us organize ourselves and distribute each member's responsibilities. This allowed us to make progress on the different activities according to the roles we defined and the planning carried out. The main difficulty we faced as a team was choosing the tools we were going to use. Some very good options required payment, while some free alternatives had significant limitations. Therefore, we had to conduct extensive research until we found free tools that met our needs. We learned how to use them and, as a team, decided to adopt them.

Adjusted or eliminated activities: Indicate the adjustments you made to your work plan or the activities you eliminated, and justify why you did so. If your work plan has not required and does not require adjustments, justify this decision based on the facilitating factors that have allowed you to carry it out as planned. We made a total of five adjustments to the work plan. Two of the changes were made because the activity development time originally defined was not appropriate. The other three activities were added because initially we had only included the development of functionalities and had not considered design, database development and integration. Therefore, we had to separate the Sprints, carrying out four instead of two, and add the missing activities. What helped us continue with the remaining activities and complete them was, as mentioned above, the methodology and planning established at the beginning of the project, which helped us organize ourselves and complete everything within the corresponding timeframe.

Activities you have not started or that are delayed: If you have not started activities or they are delayed according to your planning, indicate the reasons why you have not been able to meet those deadlines and what strategies you would use to make progress on those activities without affecting your APT project. The activities we have not yet started mainly correspond to testing and project closure, as our current planning still has us completing the final development Sprints. These activities are planned for Phase 3, when we will focus on testing, final corrections, functionality validation and delivery preparation.

If the APT Project is a group project, the names of the team members responsible for each task or activity must be indicated in this column. This will later make it possible to differentiate the evaluation of each team member.